## ONLINE NEWS GANTT CHART
ONLINE NEWS WEBSITE PROJECT
PROJECT GANTT CHART
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Gathering Requirements | 2025-02-17 | 2025-02-17 | 0 | High | 100%
Writing The Proposal | 2025-02-17 | 2025-02-18 | 1 | High | 100%
Creating Budget | 2025-02-18 | 2025-02-19 | 1 | High | 100%
Wireframing | 2025-02-20 | 2025-02-21 | 1 | Medium | 100%
UI/UX Design | 2025-02-21 | 2025-02-23 | 2 | High | 100%
Finalising Dessign | 2025-02-23 | 2025-02-25 | 2 | High | 100%
Layout And Styling (HTML/CSS) | 2025-02-26 | 2025-02-28 | 2 | High | 100%
Responsive Design (Css) | 2025-02-28 | 2025-03-02 | 2 | Medium | 100%
Interactive Elements (JS) | 2025-03-02 | 2025-03-04 | 2 | High | 100%
Database Setup | 2025-03-05 | 2025-03-07 | 2 | High | 100%
Server-Side Logic (PHP) | 2025-03-07 | 2025-03-08 | 1 | High | 100%
User Authentication | 2025-03-08 | 2025-03-09 | 1 | High | 100%
Connect Frontend and Backend | 2025-03-09 | 2025-03-10 | 1 | High | 50%
API Setup | 2025-03-11 | 2025-03-13 | 2 | High | 0%
Functionality Testing | 2025-03-13 | 2025-03-15 | 2 | High | 50%
Fixing Bugs | 2025-03-15 | 2025-03-17 | 2 | High | 50%
User Testing | 2025-03-18 | 2025-03-20 | 2 | High | 0%
Hosting Setup | 2025-03-21 | 2025-03-22 | 1 | High | 0%
Final Adjustments/Submission | 2025-03-22 | 2025-03-23 | 1 | Medium | 0%